## Sheet1
ID | Story | Estimation | Priority | Sprint | Status
2 | As a car driver, I want to create a user account so that I can be able to login and assess more features of the application | 2 | 2 | 2
3 | As a car driver, I want to see a summary of available parking space around my destination address in Tartu | 3 | 1 | 1
4 | As a car driver, I want information about parking space availability to be presented overlaid over a map, including information about the price that applies (Zone A vs B) | 3 | 1 | 1
5 | As a car driver, when I enter my intended leaving hour I want the system to also provide an estimation of the fee to be paid (per zone, hourly vs. real-time payment) | 2 | 1 | 2
6 | As a car driver I want to select between hourly or real-time payment | 2 | 2 | 2
7 | As a car driver, I want to submit a start and end of parking time. | 2 | 2 | 2
8 | The system must identify the parking space been used by the car | 3 | 4
9 | The system must block occupied parking spaces from being occupied again | 3 | 4
10 | The system must update the availability of parking space whenever a change occurs (e.g. when a car driver occupies a space, when a car driver vacates a space, a parking area is full etc). | 3 | 4
11 | As a car driver, I want to be notified about the end of my parking period 10 minutes before it ends | 5 | 4
12 | As a driver I want to extend my period before it ends | 4 | 4
13 | The system should start advertising a parking space as free(or to be free in 2 minutes) 2 minutes before the end of the paid period | 5 | 4
14 | As a car driver, when I choose hourly payment scheme, I want to get an invoice before starting a parking period(or when I start an extension period) | 3 | 3
15 | As a car driver, when I choose real-time payment scheme, I want to receive my invoice at the end of my parking period | 4 | 3
16 | As a car driver, when I'm configured to pay monthly, I want to get an invoice at the end of every month | 5 | 3
17 | As a driver I want to configure my preferred payment scheme | 3 | 3